## Sheet1
Week # | Date | Progress Presented | Assignment
? | 2020-01-22 | Overview: Project objectives and outcomes
1 | 2020-01-29 | Project High-Level Description (HLD) Development | Project Kick-off Allocate resources
2 | 2020-02-05 | HLD Review/Baseline and Requirements Development | Sprint 1 Start Web/Android Sign-up dev MySQL Tables Finalize HLD and schedule Project Management Plan (PMP)
3 | 2020-02-12 | System Requirement Documents and User Story Progress of App PMP | System Design Document (SDD) User Stories (USs)Student/Tutor sign in and Check-in system Present USs to Wang
4 | 2020-02-19 | System Design Document (SDD) User Stories (USs) Student/Tutor sign in and Check-in system Wang Requirements | Uss Baseline Draft of SDD & TP Present of USs/SDD/TP Test Plan Admin on mobile Admin functions on web Analytics and flag functions Check in system continued…
5 | 2020-02-26 | Uss Baseline Draft of SDD & TP Present of USs/SDD/TP Test Plan Admin on mobile Admin functions on web | Check in system continued…
6 | 2020-03-04 | Finalize SDD & TP Check in system continued… | Check in system continued…
7 | 2020-03-11 | End of Sprint 1 Core Functionality/ Program | Start Sprint 2: Data Analytics Administrative Features Live Testing
8 | 2020-03-18 | Data Analytics Live Testing | Data Analytics Administrative Features Live Testing
9 | 2020-03-25 | Data Analytics Administrative Features Live Testing Submit Poster | Data Analytics Live Testing
10 | 2020-04-01 |  | Data Analytics Live Testing
11 | 2020-04-08 |  | Data Analytics Live Testing
12 | 2020-04-15 |  | Data Analytics Live Testing
13 | 2020-04-22 | Data Analytics Live Testing
14 | 2020-04-29 | Research Day | Research Day