## Sheet1
Week # | Date | Progress Presented | Assignment
? | 2020-01-22 | Overview: Project objectives and outcomes
1 | 2020-01-29 | Project High-Level Description (HLD) Development | Project Kick-off Allocate resources
2 | 2020-02-05 | HLD Review/Baseline and Requirements Development | Sprint 1 Start Web/Android Sign-up dev MySQL Tables Finalize HLD and schedule Project Management Plan (PMP)
3 | 2020-02-12 | System Requirement Documents and User Story Progress of App PMP | System Design Document (SDD) User Stories (USs)Student/Tutor sign in and Check-in system Present USs to Wang
4 | 2020-02-19 | System Design Document (SDD) User Stories (USs) Student/Tutor sign in and Check-in system Wang Requirements | Uss Baseline Draft of SDD & TP Present of USs/SDD/TP Test Plan Admin on mobile Admin functions on web Analytics and flag functions
5 | 2020-02-26 | Uss Baseline Draft of SDD & TP Present of USs/SDD/TP Test Plan Admin on mobile Admin functions on web
6 | 2020-03-04
7 | 2020-03-11
8 | 2020-03-18 | End of Sprint 1
9 | 2020-03-25
10 | 2020-04-01
11 | 2020-04-08
12 | 2020-04-15
13 | 2020-04-22
14 | 2020-04-29 | Research Day | Research Day
15 | 2020-05-06
16 | 2020-05-13